## Bug Report
Bug ID | Related Test Case | Scenario ID | Bug Title | Module | Environment | Severity | Priority | Reported By | Steps to Reproduce | Expected Result | Actual Result
BUG-001 | TC-HP-011 | HP-011 | Desktops category page displays unrelated products from other categories | Navigation / Category Filter | demo.opencart.com ¦ Chrome ¦ Windows | Major | High | QA Tester | 1. Go to https://demo.opencart.com/ 2. Hover over "Desktops" in the navigation bar 3. Click on "Desktops" main category 4. Observe the product listing page | Only Desktop-related products (PCs, Mac Desktops) are displayed on the Desktops category page | Unrelated products are displayed alongside desktops: • Canon EOS 5D → belongs to Cameras • HP LP3065 → belongs to Monitors • Apple Cinema 30" → belongs to Monitors Category filter is not working correctly.
BUG-002 | TC-HP-014 | HP-014 | Laptops & Notebooks sub-category pages display 0 products despite main category showing correct items | Navigation / Sub-Category Filter | demo.opencart.com ¦ Chrome ¦ Windows | Major | High | QA Tester | 1. Go to https://demo.opencart.com/ 2. Hover over "Laptops & Notebooks" 3. Click "Laptops & Notebooks" main link → products load correctly ✅ 4. Go back to Home page 5. Hover over "Laptops & Notebooks" again 6. Click any sub-category (e.g., "Macs" or "Windows") 7. Observe the product listing page | Sub-category page displays only products belonging to that specific sub-category (e.g., "Macs" shows only Mac laptops) | Every sub-category under "Laptops & Notebooks" returns an empty product listing (0 products shown). Main category works fine — the issue is isolated to sub-category navigation. Likely cause: products are only mapped to the parent category in the backend, not assigned to individual sub-categories.

## Summary
Bug Report Summary – OpenCart Homepage
Bug Status Overview
Status | Count
Open | 2
In Progress | 0
Resolved | 0
Closed | 0
Reopen | 0
TOTAL | 2
Bug Severity Breakdown
Severity | Count
Critical | 0
Major | 2
Minor | 0
Trivial | 0
Bug Quick Reference
Bug ID | Title | Severity | Priority | Status
BUG-001 | Desktops page shows unrelated products (Camera, Monitor) | Major | High | Open
BUG-002 | Laptops & Notebooks sub-categories show 0 products | Major | High | Open